## Introduction
[Insert Department/Project Logo] |  | [Insert Department Name] [Insert Project Name]
Introduction to the RACI Matrix Template
The RACI Matrix describes the participation by various roles for completing deliverables for a project. It is especially useful in clarifying roles and responsibilities where cross-functional roles or processes exist. It shows the major work that needs to be completed and the associated responsibilities for that work.
The purpose of the RACI Matrix is to document:
· The deliverables associated with each process phase
· Any applicable templates for each of the deliverables
· The owner of the template
· The specific responsibility assignments in regard to who makes the formal decision to approve or reject the deliverable
· Who can formally sign showing support or dissent in regards to the deliverable
· Who is responsible for creating the deliverable
· Who could be invited, but not required, to provide their input to the deliverable
· Who needs to be informed regarding the deliverable
This RACI Matrix Template with Instructions contains directions for properly initiating and maintaining the RACI Matrix. As you complete the template, please remember to delete all instructional text (including this "Introduction" tab and the "Instructions" tab) and update the header and footer. Update the document to a minor version (e.g., 1.1, 1.2) when minimal changes are made and a major version (e.g., 2.0, 3.0) when significant change are made.
Template style conventions are as follows:
Style | Convention
Normal text | Indicates placeholder text that can be used for any project
[Instructional text in brackets] | [Indicates text that is to be replaced/edited/deleted by document author]
Example text in italics | Indicates example text that might be replaced/edited/deleted by user
Project Sample Library: The CA-PMF has a Project Sample Library that contains real-world project artifacts from approved projects that you can reference to help you complete CA-PMF templates. Visit the CA-PMF website to access the Project Sample Library.
CA-PMF website: | http://capmf.cio.ca.gov/

## Instructions
[Insert Department/Project Logo] |  |  | [Insert Department Name] [Insert Project Name]
RACI Matrix Template Instructions
1 Introduction
The RACI Matrix links project resources to project deliverables by assigning the resource a particular responsibility or responsibilities in the preparation of that deliverable. Throughout the project life cycle, the RACI Matrix can be utilized in conjunction with the Project Management Plan (PMP) to help manage scope, schedule, resources, quality, and communication. Your organization may already possess one or more templates that may identify different deliverables, stakeholders, or responsibility assignment standards based on project type, size, or other factors. If an appropriate template does not exist, use this RACI Matrix.
The RACI MAtrix consists of the following attributes. Attribute descriptions are provided to help understand usage.
• Deliverable – The specific named deliverable to which resource responsibilities are being assigned. Each project deliverable should be entered on an individual row.
• Phase Established – The project phase in which the deliverable will be produced. Project phases include Concept, Initiating, Planning, Executing, and Closing.
• Applicable Template – The template that will be used to develop the deliverable. As an example, the CA-PMF provides a suite of templates for developing project management deliverables.
• Template Owner – The entity responsible for developing, publishing and maintaining the referenced template.
• Stakeholder List – A project-specific list of stakeholders involved in developing and approving project deliverables.
• Notes – Explanations and clarifications regarding the deliverables, stakeholders, and assigned responsibilities.
2 Creating the RACI
2.1 Identify Deliverables
List all of the project deliverables in the vertical axis (left-hand column) starting with deliverables identified in the WBS. A comprehensive list of typical deliverables is built-in to the template, however each project is unique and will most likely require additional deliverables be added to the RACI Matrix. Insert these additional deliverables then populate the associated cells for each to include the Phase Established, Applicable Template, Template Owner and role responsibility. A note field is provided to capture additional information as needed.
2.2 Identify Resources
Project resources are entered in the columns adjacent to the Template Owner column. To identify resources for the RACI Matrix, start with the project Stakeholder Registry and/or organizational chart in determining the resources that will be responsible for various delivery aspects with the deliverables. Overall definitions of project roles can be found in the Definitions of Project Roles section in the CA-PMF Additional Resources chapter. The template list shows some common project resources, but the table should be modified to suit project needs.
2.3 Assign Responsibilities
The Responsibilities Table below defines the responsibilities associated with the development and approval of project deliverables. Each responsibility has a designator which is used in the RACI Matrix at the intersection of a resource column and deliverable row. The designator indicates the resource's responsibility with respect to the particular deliverable. It is especially important that each deliverable have at least one resource assigned to creating the deliverable and at least one resource assigned to approving it. Thus, every deliverable should have an A and an R entry. It is possible that a particular individual could have multiple responsibilities with regard to a particular deliverable. It is also possible that an identified resource has no responsibility for a given deliverable and in that case, the intersection is left blank. Individual projects may have additional resources and designators and should adjust the table accordingly.
Responsibility | Designator | Responsibility Definition
Responsible | R | Bears some responsibility for creating the deliverable
Approve | A | Makes the formal decision to approve or deny (one per deliverable)
Consulted | C | Specifically invited, but not required, to provide input
Informed | I | Notified of updates to the deliverable (especially approval)
Sign | S | Formally indicates support or dissent (unanimity not required)
No Role | Blank | Has no role in the development or approval of the deliverable
2.4 Provide additional Information
Add any additional explanatory or clarifying information needed in the notes column.
3 Example
An example has been provided on the template. In the example given, the responsibilities related to the development of a Project Concept are identified. The Project Manager (PM) has been assigned responsibility for developing the concept. To complete it, the PM consults with a number of Stakeholders, as indicated, including the Business Owner, the Project Spnsors, the System Architect, the Information Security Officer, and Legal Counsel. The Project Director approves the concept. Other resources are kept informed regarding efforts to develop and approve the project concept. Some resources have no responsibilities associated with the concept development activities.

## RACI
[Insert Department/Project Logo] | [21 empty] | [Insert Department Name] [Insert Project Name]
Legend: "R" – Responsible "A" – Approve “C” – Consulted “I” – Informed "S" – Sign Deliverables | Phase Established | Applicable Template | Template Owner | Project Team | [11 empty] | Advisory Project Team Members | [5 empty] | Notes
|  |  |  | Project Sponsor | IT Sponsor (CIO) | Project Director | Project Manager | Business Owner(s) | IT Product Owner(s) | Organizational Change Manager | System Architect | Procurement Manager | Contract Manager | Implementation Manager | Information Security Officer | Operation Manager | IV&V | Legal Counsel | Department of Technology (Data Center) | Department of Finance | Department of Technology
[Add additional deliverables as necessary grouping them with the phase in which they will be established] | [Identify the phase for the added deliverable] | [Identify any templates that are related to the added deliverable] | [Identify the owner of the template]
Project Concept | Concept | Concept Development and Readiness Assessment | CA-PMF | C,S | C | A,S | R | C |  |  | C | I | I |  | C | I |  | C
Stage 1 Business Analysis | Concept | S1BA Form | PAL
CConcept Process Phase Completion | Concept | Concept Process Phase Checklist | CA-PMF
Project Charter | Initiating | Project Charter | CA-PMF
Project Priorities Assessment | Initiating | Project Priorities Assessment | CA-PMF
RACI Matrix | Initiating | RACI Matrix | CA-PMF
Stakeholder Register | Initiating | Stakeholder Register | CA-PMF
Project Status Reports | Initiating | Project Status Reports | Oversight
Project Document Approval | Initiating | Project Document Approval Template | CA-PMF
Initiating Process Phase Completion | Initiating | Initiating Process Phase Checklist | CA-PMF
Change Control Management Plan | Planning | Change Control Management Plan | CA-PMF
Change Request Analysis | Planning | Change Request Analysis | CA-PMF
Change Request Form | Planning | Change Request Form | CA-PMF
Change Request Summary Report | Planning | Change Request Summary Report | CA-PMF
Communications Management Plan | Planning | Communications Management Plan | CA-PMF
Complexity Assessment | Planning | Complexity Assessment | Oversight
Corrective Action Plan | Planning | Corrective Action Plan | CA-PMF
Cost Management Plan | Planning | Cost Management Plan | CA-PMF
Human Resources Management Plan | Planning | Human Resources Management Plan | CA-PMF
Issue Log | Planning | Issue Log | CA-PMF
Implementation Management Plan | Planning | Implementation Management Plan | CA-PMF
Issue Management Plan | Planning | Issue Management Plan | CA-PMF
Maintenance and Operations Transition Plan | Planning | Maintenance and Operations Transition Plan | CA-PMF
Meeting Agenda and Notes | Planning | Meeting Agenda and Notes Template | CA-PMF
Procurement Management Plan | Planning | Procurement Management Plan | CA-PMF
Project Management Plan | Planning | Project Management Plan | CA-PMF
Project Organization Chart | Planning | Project Organization Chart | CA-PMF
Quality Management Plan | Planning | Quality Management Plan | CA-PMF
Requirements Management Plan | Planning | Requirements Management Plan | CA-PMF
Requirements Traceability Matrix | Planning | Requirements Traceability Matrix | CA-PMF
Risk Assessment | Planning | Risk Assessment | Oversight
Risk Management Plan | Planning | Risk Management Plan | CA-PMF
Risk Register | Planning | Risk Register | CA-PMF
Schedule Management Plan | Planning | Schedule Management Plan | CA-PMF
Scope Management Plan | Planning | Scope Management Plan | CA-PMF
Skills Assessment | Planning | Skills Assessment | CA-PMF
Stakeholder Management Plan | Planning | Stakeholder Management Plan | CA-PMF
Work Breakdown Structure | Planning | Work Breakdown Structure | CA-PMF
Governance Management Plan | Planning | Governance Management Plan | CA-PMF
PAL documents | Planning | S2AA, S3SD, S4PR | PAL
Planning Process Phase Completion | Planning | Planning Process Phase Checklist | CA-PMF
Deliverable Expectations | Executing | Deliverable Expectation Document | CA-PMF
Work Authorizations | Executing | Work Authorization | CA-PMF
Process Improvement Plan | Executing | Process Improvement Plan | CA-PMF
Formal Product Acceptance | Executing | Formal Product Acceptance | CA-PMF
Sponsorship Commitment Survey | Executing | Sponsorship Commitment Survey | CA-PMF
Team Effectiveness Survey | Executing | Team Effectiveness Survey | CA-PMF
Executing Process Phase Completion | Executing | Executing Process Phase Checklist | CA-PMF
Lessons Learned | Closing | Lessons Learned | CA-PMF
Project Closeout Report | Closing | Project Closeout Report | CA-PMF
Closing Process Phase Completion | Closing | Closing Process Phase Checklist | CA-PMF
[Assign responsibilities by stakeholder for each added deliverable. Add notes as necessary.]